## Public Realm Timeline
Project | Description | Autumn 2019 | Winter 2019/2020 | Spring 2020 | Summer 2020 | Autumn 2020 | Winter 2020/2021 | Spring 2021 | Summer 2021
Current Works & Community Engagement
Crystal Gardens | Landscaping and refreshed planting around the Crystal building to beautify and provide space for relaxation
Silvertown Quays | Enabling works to improve site access, undertake vegetation clearance and maintenance works to Silo D
Royal Albert Dock (Dock Edge) | Dock edge path upgrade and reopening between Newham/Dockside and the UTC/UEL to connect the entire north side of Royal Albert Dock
Thames Barrier Park Café | Complete refurbishment of the café building to support increased use and new café operator
Royal Albert Dock (Meanwhile Plots) | Enabling works to land between ABP phase one and UTC/UEL to support meanwhile use including Soldier of Orange
The Lawns - Dockside | Enabling works to support meanwhile uses on the lawns to the west of Newham/Dockside
Beckton Park DLR | Landscaping improvements to the northern entrance to the station
Design Guides Programme: Community Engagement Plan - Phase 0 | Ensure the conversation with the community continues from the 2019 engagement
Design Guides Programme: Community Engagement Plan - Phase 1 | Re-start the conversation, gain a greater understanding of people's use and experience of key routes and places
Design Guides Programme - Phase 1 | Establishing guiding principles to upgrade the public realm, and identify key locations for lighting, landscaping and wayfinding interventions
Brompton Bike Docking Station | Two new docking stations for Brompton Bike Hire, one at the Crystal and one at Newham/Dockside
Design Guides Programme: Community Engagement Plan - Phase 2 | Engage the community in the design of public realm elements and their application in specific locations
Design Guides Programme - Phase 2 | Design in detail a set of lighting, landscaping and wayfinding elements, to establish a consistent character across the Royal Docks; and apply these designs to specific locations
Forthcoming Works
Design Guides Programme | Production of final public facing documents
Thames Barrier Park Refresh | Works carried out on feedback received from the public consultation to improve lighting, parking, security, opening hours amongst other requests
Royal Victoria Dock - Bridge Lifts | Feasability for the replacement of the lifts at the Royal Victoria Dock footbridge
Floating Gardens | Pilot project to create a small floating garden at the western end of Royal Victoria Dock with the gardens planted by the community
Tree Planting Programme | Tree planting across the Royal Docks as part of the Urban Tree Challenge Fund following a public consultation
Connaught Crossing | Improvements to the surfacing and lighting across the lower level pedestrian and cycle spaces
Beckton Park Links | Options to improve links between Beckton Park and the Royal Docks by upgrading crossings and signage
Future Project Areas *TBC
Royal Victoria Dock | Wide ranging review into the use on and around Royal Victoria Dock
Connaught Bridge North | Potential highways realignment and development
North Woolwich | Programme of existing projects being led by Newham
KEY
Current Works
Community Engagement